# STATEMENT OF WORK TEMPLATE

Template Version: 1.0

Document Type: Generic Statement of Work

Effective Date: January 22, 2024

# METADATA TABLE

Contract Type: Statement of Work (SOW)

Vendor: Generic

Effective Date: January 22, 2024

Client: Finance Solutions Ltd

Project Code: FS-DA-2024-003

Document Version: 1.0

Last Updated: January 19, 2024

Prepared By: Thomas Anderson

Approved By: Diana Prince

# 1. PROJECT OVERVIEW

This Statement of Work ("SOW") sets forth the terms and conditions under which Analytics Pro Inc. ("Vendor") will provide services to Finance Solutions Ltd ("Client") for the Data Analytics Platform project. This SOW is governed by the Master Services Agreement between the parties dated October 20, 2023 and incorporates all terms and conditions contained therein.

The project objective is to develop and implement a comprehensive data analytics platform to enable real-time financial reporting and predictive analytics capabilities. The Vendor shall provide professional services including but not limited to data architecture design, ETL development, dashboard creation, and analytics model implementation in accordance with the specifications, timelines, and deliverables outlined in this document.

This engagement is expected to commence on January 22, 2024 and conclude on October 22, 2024, subject to the terms and conditions set forth herein. The total estimated value of this engagement is $350,000 as detailed in the payment terms section.

# 2. SCOPE OF WORK

The Vendor shall perform the following services and activities:

2.1 Primary Services

Analytics Pro Inc. shall provide data analytics platform development including but not limited to:

Data architecture design and database optimization

ETL pipeline development and automation

Interactive dashboard and reporting development

Predictive analytics model creation and deployment

2.2 Secondary Services

## Additional services may include:

Data quality assessment and cleansing procedures

User training on analytics tools and dashboards

Performance monitoring and optimization

45-day post-implementation support

2.3 Exclusions

The following items are specifically excluded from this SOW:

Data warehouse infrastructure costs

Third-party analytics software licensing

Historical data migration beyond 2 years

Any services not explicitly included in this SOW shall require a separate written agreement or change order as outlined in Section 9.

# 3. DELIVERABLES

The Vendor shall provide the following deliverables according to the specified timeline:

3.1 Phase 1 Deliverables

Data Architecture Document: Comprehensive platform design - Due: February 22, 2024

ETL Design Specifications: Data processing workflows - Due: March 8, 2024

Dashboard Mockups: User interface designs and wireframes - Due: March 22, 2024

3.2 Phase 2 Deliverables

Functional Analytics Platform: Core system implementation - Due: July 15, 2024

Predictive Models: Machine learning algorithms and forecasting tools - Due: August 15, 2024

3.3 Final Deliverables

Production Analytics Platform: Fully deployed and operational system - Due: September 30, 2024

User Training Program: Comprehensive training materials and sessions - Due: October 22, 2024

All deliverables shall be provided in the format specified by the Client and shall meet the acceptance criteria outlined in Section 6.

# 4. PROJECT TIMELINE

The project shall be executed according to the following timeline:

Phase 1: Project Initiation (January 22, 2024 - March 22, 2024)

Week 1-2: Project kickoff and requirements gathering

Week 3-4: Initial analysis and planning

Week 5-6: Architecture design and prototyping

Phase 2: Implementation (March 23, 2024 - August 15, 2024)

Week 7-10: Platform development and ETL implementation

Week 11-12: Testing and validation

Week 13-14: Analytics model development and integration

Phase 3: Project Closure (August 16, 2024 - October 22, 2024)

Week 15-16: Final deliverables and handover

Week 17-18: Project closure and knowledge transfer

## Key milestones include:

Data Architecture Approval: February 22, 2024

Platform Beta Release: June 15, 2024

Production Go-Live: September 30, 2024

# 5. RESOURCE ALLOCATION

5.1 Vendor Resources

The Vendor shall assign the following resources to this project:

Project Manager: Rachel Green - 20 hours/week

Technical Lead: Alex Turner - 35 hours/week

Senior Consultant: Maria Gonzalez - 40 hours/week

Junior Consultant: Kevin Park - 30 hours/week

5.2 Client Resources

## The Client shall provide the following resources:

Project Sponsor: Diana Prince

Business Analyst: Thomas Anderson

Technical Contact: Sarah Mitchell

End User Representatives: Finance and Accounting Teams

5.3 Resource Responsibilities

All Vendor resources shall be qualified professionals with appropriate experience and certifications. The Vendor shall ensure adequate resource availability throughout the project duration and shall notify the Client immediately of any resource changes.

# 6. ACCEPTANCE CRITERIA

6.1 Deliverable Acceptance

Each deliverable shall be subject to Client review and acceptance. The Client shall have 5 business days from receipt to review and either accept or reject each deliverable with specific written feedback.

6.2 Acceptance Process

Vendor submits deliverable with completion notice

Client reviews deliverable against specified criteria

Client provides written acceptance or rejection with detailed feedback

If rejected, Vendor has 3 business days to address issues

Process repeats until deliverable is accepted

6.3 Acceptance Criteria Standards

All deliverables must meet the following minimum standards:

Completeness according to specifications

Quality standards as defined in project requirements

Compliance with applicable regulations and standards

Documentation requirements as specified

# 7. ASSUMPTIONS AND DEPENDENCIES

7.1 Assumptions

## This SOW is based on the following assumptions:

Financial data sources are accessible and well-documented

Current reporting requirements are stable and defined

Analytics platform will integrate with existing systems

Performance requirements can be met with proposed architecture

7.2 Dependencies

## Project success is dependent upon:

Timely provision of Client resources and information

Access to required systems and environments

Data quality meets minimum standards for analytics

Client approval of dashboard designs and user interfaces

Availability of subject matter experts for requirements validation

7.3 Risk Mitigation

The parties acknowledge that changes to assumptions or dependencies may impact project scope, timeline, or cost and agree to address such changes through the change management process outlined in Section 9.

# 8. PAYMENT TERMS

8.1 Total Contract Value

The total value of this engagement is $350,000 payable according to the schedule below.

8.2 Payment Schedule

Phase 1 Completion: $120,000 due within 30 days of acceptance

Phase 2 Completion: $180,000 due within 30 days of acceptance

Final Deliverables: $50,000 due within 30 days of project completion

8.3 Invoicing

The Vendor shall submit invoices monthly for work completed. All invoices shall include:

Detailed description of work performed

Hours worked by resource type

Deliverables completed

Project code reference: FS-DA-2024-003

Payment terms are Net 30 days from receipt of properly submitted invoice.

8.4 Expenses

Pre-approved expenses shall be reimbursed at cost with appropriate documentation. Travel expenses require prior written approval from the Client.

# 9. CHANGE MANAGEMENT

9.1 Change Request Process

Any changes to this SOW must be documented through a formal change request process including:

Written description of proposed change

Impact analysis on scope, timeline, and cost

Client approval before implementation

Updated SOW documentation

9.2 Change Authorization

Changes exceeding $12,000 require written approval from Diana Prince. Minor changes may be approved by the designated project manager.

9.3 Change Implementation

Approved changes shall be implemented according to revised timeline and specifications. No work on changes shall commence without proper authorization.

# 10. TERMS AND CONDITIONS

10.1 Governing Agreement

This SOW is governed by the Master Services Agreement between the parties dated October 20, 2023. In case of conflict, the MSA shall take precedence.

10.2 Confidentiality

Both parties acknowledge that confidential information may be exchanged during this engagement and agree to maintain strict confidentiality according to the terms of the MSA.

10.3 Intellectual Property

All work product created under this SOW shall be owned by the Client upon full payment. The Vendor retains rights to general methodologies and know-how.

10.4 Limitation of Liability

The Vendor's liability under this SOW shall not exceed the total value of the contract. Neither party shall be liable for indirect, consequential, or punitive damages.

10.5 Termination

Either party may terminate this SOW with 30 days written notice. Upon termination, the Vendor shall be compensated for work completed and accepted.

10.6 Force Majeure

Neither party shall be liable for delays or failures due to circumstances beyond their reasonable control including but not limited to acts of God, government actions, or natural disasters.

# SIGNATURE BLOCK

CLIENT: Finance Solutions Ltd

By: _________________________    Date: ___________

Name: Diana Prince

Title: Chief Financial Officer

VENDOR: Analytics Pro Inc.

By: _________________________    Date: ___________

Name: Rachel Green

Title: Project Manager

## Document Control:

Template ID: TYPE_SOW_Standard_v1

Version: 1.0

Created: January 19, 2024

Last Modified: January 19, 2024

Next Review: October 22, 2024