# CHANGE ORDER TEMPLATE

Template Version: 1.0

Document Type: Generic Change Order

Effective Date: February 5, 2024

# METADATA TABLE

Contract Type: Change Order

Vendor: Generic

Effective Date: February 5, 2024

Client: GlobalTech Inc

Project Code: GT-CM-2024-002

Original SOW Reference: SOW-GT-CM-2024-002

Change Order Number: CO-002

Document Version: 1.0

Last Updated: February 2, 2024

Prepared By: Amanda Foster

Approved By: Robert Martinez

# 1. REFERENCE TO ORIGINAL SOW

This Change Order ("Change Order") modifies the Statement of Work between GlobalTech Inc ("Client") and DataFlow Solutions ("Vendor") dated January 18, 2024 and identified as SOW-GT-CM-2024-002 ("Original SOW").

1.1 Original SOW Details

Original SOW Title: Cloud Migration Project

Original SOW Date: January 18, 2024

Original SOW Value: $420,000

Original Project Duration: January 18, 2024 to September 18, 2024

Original Project Manager: Carlos Mendez

1.2 Change Order Authority

This Change Order is issued pursuant to Section 9 (Change Management) of the Original SOW and the Master Services Agreement between the parties dated November 15, 2023.

1.3 Precedence

This Change Order shall be incorporated into and become part of the Original SOW. In case of conflict between this Change Order and the Original SOW, the terms of this Change Order shall take precedence for the specific items addressed herein.

# 2. DESCRIPTION OF CHANGE

2.1 Summary of Change

This Change Order addresses the addition of disaster recovery capabilities and enhanced security compliance requirements that were identified as critical business needs during the initial migration planning phase.

2.2 Detailed Change Description

## The specific changes to be implemented include:

2.2.1 Scope Modifications

Disaster Recovery Implementation: Multi-region backup and failover capabilities with automated recovery procedures

Enhanced Security Compliance: Implementation of SOC 2 Type II compliance framework and additional security controls

Performance Optimization: Advanced monitoring and auto-scaling configuration for improved system performance

2.2.2 Deliverable Changes

Modified Deliverable: Security Framework Document

Original Specification: Basic cloud security implementation plan

New Specification: Comprehensive SOC 2 compliance framework with detailed controls documentation

Impact: Additional 3 weeks for compliance assessment and documentation

New Deliverable: Disaster Recovery System

Specification: Multi-region backup solution with automated failover and recovery testing procedures

Due Date: August 15, 2024

Acceptance Criteria: Tested disaster recovery system meeting RTO of 4 hours and RPO of 1 hour

2.2.3 Resource Changes

## - Additional Resources Required:

Security Compliance Specialist: 200 hours over 10 weeks

Disaster Recovery Engineer: 180 hours over 9 weeks

## - Resource Reallocation:

Technical Lead: Increased from 35 to 40 hours/week for weeks 12-20

# 3. REASON FOR CHANGE

3.1 Change Justification

This change is necessary due to new regulatory compliance requirements and business continuity needs identified by the client's risk management team during the project planning phase.

3.2 Business Impact

The change addresses the following business needs:

Regulatory compliance with industry standards for data protection and security

Business continuity assurance through robust disaster recovery capabilities

Enhanced system performance and reliability for critical business operations

3.3 Risk Mitigation

## This change helps mitigate the following risks:

Compliance Risk: SOC 2 implementation ensures regulatory compliance and customer trust

Business Continuity Risk: Disaster recovery system protects against data loss and extended downtime

3.4 Stakeholder Request

## This change was requested by:

Requestor: Robert Martinez

Title: Chief Information Officer

Date of Request: January 30, 2024

Request Reference: CR-2024-002

# 4. IMPACT ON SCOPE

4.1 Scope Additions

The following items are added to the project scope:

Disaster Recovery System: Multi-region backup infrastructure with automated failover capabilities (Effort: 180 hours)

SOC 2 Compliance Implementation: Security controls, policies, and audit preparation (Effort: 200 hours)

Performance Monitoring Suite: Advanced monitoring, alerting, and auto-scaling configuration (Effort: 100 hours)

4.2 Scope Modifications

## The following existing scope items are modified:

## - Security Framework Document:

Original: Basic cloud security planning

Modified: Comprehensive SOC 2 compliance framework with detailed implementation guide

Effort Change: Additional 60 hours for compliance documentation and assessment

4.3 Scope Deletions

The following items are removed from the project scope:

Basic Monitoring Setup: Simple CloudWatch configuration (Effort Savings: 40 hours)

Standard Backup Configuration: Basic daily backup setup (Effort Savings: 30 hours)

4.4 Net Scope Impact

Total Scope Additions: 480 hours of specialized work

Total Scope Modifications: 60 hours additional effort

Total Scope Deletions: 70 hours effort savings

Net Scope Change: 470 hours additional effort

# 5. IMPACT ON TIMELINE

5.1 Schedule Changes

The following schedule modifications are required:

5.1.1 Milestone Adjustments

## - Security Framework Approval:

Original Date: March 20, 2024

New Date: April 10, 2024

Reason: Additional time needed for SOC 2 compliance assessment and documentation

## - Production Cutover:

Original Date: August 30, 2024

New Date: September 15, 2024

Reason: Additional testing time required for disaster recovery validation

5.1.2 Phase Duration Changes

## - Phase 2 Implementation:

Original Duration: 15 weeks

New Duration: 18 weeks

Impact: Extended to accommodate disaster recovery setup and compliance implementation

5.2 Critical Path Impact

## This change affects the critical path as follows:

Disaster recovery testing becomes critical path activity requiring coordination with production systems

New Critical Path Activities: DR system setup, compliance audit preparation, and performance optimization

Risk to Overall Timeline: Low to medium risk due to dependency on third-party compliance auditors

5.3 Revised Project Timeline

Original Project End Date: September 18, 2024

New Project End Date: October 18, 2024

Total Schedule Impact: 4 weeks extension

# 6. IMPACT ON BUDGET

6.1 Cost Changes

The financial impact of this change order is as follows:

6.1.1 Additional Costs

Labor Costs: $115,000

Security Compliance Specialist: 200 hours at $200/hour = $40,000

Disaster Recovery Engineer: 180 hours at $185/hour = $33,300

Technical Lead Additional Hours: 200 hours at $150/hour = $30,000

Project Management Overhead: 70 hours at $165/hour = $11,550

Material Costs: $8,000 (additional AWS services for DR)

Travel and Expenses: $4,000

Other Costs: $3,000 (compliance audit and certification fees)

6.1.2 Cost Savings

Reduced Labor: $10,500 (70 hours at $150/hour for removed scope items)

Reduced Materials: $2,000

Other Savings: $500

6.2 Net Financial Impact

Total Additional Costs: $130,000

Total Cost Savings: $13,000

Net Change to Contract Value: $117,000

6.3 Revised Contract Value

Original Contract Value: $420,000

Change Order Value: $117,000

New Total Contract Value: $537,000

6.4 Payment Terms for Change Order

Payment for this change order shall be made according to the following schedule:

Compliance Milestone: $60,000 due upon SOC 2 readiness assessment completion

DR Implementation: $40,000 due upon disaster recovery system acceptance testing

Final Payment: $17,000 due upon completion of all change order deliverables

# 7. REVISED DELIVERABLES

7.1 Updated Deliverable Schedule

The following deliverables are affected by this change:

7.1.1 Modified Existing Deliverables

## - Security Framework Document:

Original Due Date: March 20, 2024

New Due Date: April 10, 2024

Specification Changes: Enhanced to include SOC 2 compliance framework and detailed security controls

7.1.2 New Deliverables

## - Disaster Recovery System:

Description: Multi-region backup and failover system with automated recovery procedures and testing protocols

Due Date: August 15, 2024

Acceptance Criteria: Functional DR system meeting RTO/RPO requirements with successful failover testing

## - SOC 2 Compliance Package:

Description: Complete compliance documentation, policies, and audit-ready security controls implementation

Due Date: September 1, 2024

Acceptance Criteria: SOC 2 Type II audit readiness with all required controls implemented and documented

7.2 Deliverable Dependencies

The revised deliverables have the following dependencies:

Disaster recovery system depends on completion of primary cloud infrastructure migration

SOC 2 compliance package depends on security framework implementation and policy approval

Performance optimization depends on baseline system performance data collection

7.3 Quality Standards

All revised and new deliverables shall meet the same quality standards as specified in the Original SOW, with the following additions:

Disaster recovery system must meet specified RTO and RPO requirements under testing conditions

SOC 2 compliance implementation must pass pre-audit assessment by certified auditor

# 8. APPROVAL AND AUTHORIZATION

8.1 Change Order Authorization

This Change Order requires approval from the following authorized representatives:

8.1.1 Client Authorization

Primary Approver: Robert Martinez, Chief Information Officer

Secondary Approver: Amanda Foster, Project Manager

Budget Authority: Robert Martinez, Chief Information Officer

8.1.2 Vendor Authorization

Project Manager: Carlos Mendez, Project Manager

Account Manager: Patricia Lee, Account Manager

Executive Sponsor: Mark Stevens, Vice President

8.2 Approval Process

This Change Order follows the approval process outlined in Section 9.2 of the Original SOW:

1. Change request submitted by Robert Martinez

2. Impact analysis completed by Carlos Mendez

3. Review and approval by authorized representatives

4. Implementation upon full execution

8.3 Implementation Timeline

## Upon full execution of this Change Order:

Implementation Start Date: February 8, 2024

First Modified Deliverable Due: April 10, 2024

Change Order Completion: October 18, 2024

8.4 Communication Plan

All stakeholders will be notified of this change according to the project communication plan, including:

Project team notification: February 6, 2024

Stakeholder briefing: February 8, 2024

Updated project documentation: February 12, 2024

# SIGNATURE BLOCK

CLIENT: GlobalTech Inc

By: _________________________    Date: ___________

Name: Robert Martinez

Title: Chief Information Officer

Budget Authority: _________________________    Date: ___________

Name: Robert Martinez

Title: Chief Information Officer

VENDOR: DataFlow Solutions

By: _________________________    Date: ___________

Name: Carlos Mendez

Title: Project Manager

Project Manager: _________________________    Date: ___________

Name: Carlos Mendez

Title: Project Manager

## Document Control:

Template ID: TYPE_CHANGEORDER_Standard_v1

Version: 1.0

Original SOW Reference: SOW-GT-CM-2024-002

Change Order Number: CO-002

Created: February 2, 2024

Last Modified: February 2, 2024

Next Review: October 18, 2024