# CHANGE ORDER TEMPLATE

Template Version: 1.0

Document Type: Generic Change Order

Effective Date: February 1, 2024

# METADATA TABLE

Contract Type: Change Order

Vendor: Generic

Effective Date: February 1, 2024

Client: Acme Corp

Project Code: AC-DT-2024-001

Original SOW Reference: SOW-AC-DT-2024-001

Change Order Number: CO-001

Document Version: 1.0

Last Updated: January 30, 2024

Prepared By: Sarah Johnson

Approved By: Michael Chen

# 1. REFERENCE TO ORIGINAL SOW

This Change Order ("Change Order") modifies the Statement of Work between Acme Corp ("Client") and TechSolutions Inc. ("Vendor") dated January 15, 2024 and identified as SOW-AC-DT-2024-001 ("Original SOW").

1.1 Original SOW Details

Original SOW Title: Digital Transformation Phase 1

Original SOW Date: January 15, 2024

Original SOW Value: $275,000

Original Project Duration: January 15, 2024 to July 15, 2024

Original Project Manager: David Rodriguez

1.2 Change Order Authority

This Change Order is issued pursuant to Section 9 (Change Management) of the Original SOW and the Master Services Agreement between the parties dated December 1, 2023.

1.3 Precedence

This Change Order shall be incorporated into and become part of the Original SOW. In case of conflict between this Change Order and the Original SOW, the terms of this Change Order shall take precedence for the specific items addressed herein.

# 2. DESCRIPTION OF CHANGE

2.1 Summary of Change

This Change Order addresses the addition of advanced analytics capabilities and mobile application development to the existing Digital Transformation project scope.

2.2 Detailed Change Description

## The specific changes to be implemented include:

2.2.1 Scope Modifications

Addition of Real-time Analytics Dashboard: Development of executive dashboard with KPI tracking and real-time data visualization

Mobile Application Development: Creation of companion mobile app for iOS and Android platforms

Enhanced Data Integration: Additional API integrations with third-party business systems

2.2.2 Deliverable Changes

Modified Deliverable: Technical Architecture Document

Original Specification: Basic cloud architecture design

New Specification: Enhanced architecture including analytics platform and mobile backend

Impact: Additional 2 weeks for comprehensive design

New Deliverable: Mobile Application Package

Specification: Native iOS and Android applications with core functionality

Due Date: June 30, 2024

Acceptance Criteria: App store ready applications with full testing documentation

2.2.3 Resource Changes

## - Additional Resources Required:

Mobile Developer: 160 hours over 8 weeks

Data Analytics Specialist: 120 hours over 6 weeks

## - Resource Reallocation:

Senior Consultant: Increased from 40 to 45 hours/week for weeks 10-16

# 3. REASON FOR CHANGE

3.1 Change Justification

This change is necessary due to evolving business requirements identified during the initial project phase and competitive market pressures requiring enhanced mobile presence.

3.2 Business Impact

The change addresses the following business needs:

Improved executive visibility into business operations through real-time analytics

Enhanced customer engagement through mobile application access

Competitive advantage through advanced data-driven decision making capabilities

3.3 Risk Mitigation

## This change helps mitigate the following risks:

Market Competition Risk: Mobile app provides competitive differentiation in customer service

Data Visibility Risk: Real-time analytics enable proactive business decision making

3.4 Stakeholder Request

## This change was requested by:

Requestor: Michael Chen

Title: Chief Technology Officer

Date of Request: January 25, 2024

Request Reference: CR-2024-001

# 4. IMPACT ON SCOPE

4.1 Scope Additions

The following items are added to the project scope:

Real-time Analytics Dashboard: Development of web-based dashboard with 15 key performance indicators and automated reporting (Effort: 120 hours)

Mobile Application Development: Native iOS and Android apps with user authentication, data access, and push notifications (Effort: 200 hours)

Enhanced API Integration: Additional integrations with CRM, ERP, and marketing automation systems (Effort: 80 hours)

4.2 Scope Modifications

## The following existing scope items are modified:

## - Technical Architecture Document:

Original: Basic cloud migration architecture

Modified: Comprehensive architecture including analytics platform, mobile backend, and enhanced integrations

Effort Change: Additional 40 hours for expanded design work

4.3 Scope Deletions

The following items are removed from the project scope:

Basic Reporting Module: Simple report generation functionality (Effort Savings: 60 hours)

Legacy System Documentation: Detailed documentation of old systems (Effort Savings: 40 hours)

4.4 Net Scope Impact

Total Scope Additions: 400 hours of development work

Total Scope Modifications: 40 hours additional effort

Total Scope Deletions: 100 hours effort savings

Net Scope Change: 340 hours additional effort

# 5. IMPACT ON TIMELINE

5.1 Schedule Changes

The following schedule modifications are required:

5.1.1 Milestone Adjustments

## - Architecture Approval:

Original Date: March 15, 2024

New Date: March 29, 2024

Reason: Additional time needed for expanded architecture design

## - System Go-Live:

Original Date: June 30, 2024

New Date: July 15, 2024

Reason: Additional development time for mobile applications and analytics

5.1.2 Phase Duration Changes

## - Phase 2 Implementation:

Original Duration: 11 weeks

New Duration: 13 weeks

Impact: Extended to accommodate mobile development and analytics implementation

5.2 Critical Path Impact

## This change affects the critical path as follows:

Mobile application development becomes new critical path activity requiring parallel development streams

New Critical Path Activities: Mobile app design, development, testing, and app store submission

Risk to Overall Timeline: Medium risk due to app store approval process variables

5.3 Revised Project Timeline

Original Project End Date: July 15, 2024

New Project End Date: August 15, 2024

Total Schedule Impact: 4 weeks extension

# 6. IMPACT ON BUDGET

6.1 Cost Changes

The financial impact of this change order is as follows:

6.1.1 Additional Costs

Labor Costs: $85,000

Mobile Developer: 160 hours at $150/hour = $24,000

Data Analytics Specialist: 120 hours at $175/hour = $21,000

Senior Consultant Additional Hours: 240 hours at $125/hour = $30,000

Project Management Overhead: 80 hours at $125/hour = $10,000

Material Costs: $5,000

Travel and Expenses: $3,000

Other Costs: $2,000 (app store fees and testing devices)

6.1.2 Cost Savings

Reduced Labor: $12,500 (100 hours at $125/hour for removed scope items)

Reduced Materials: $1,500

Other Savings: $1,000

6.2 Net Financial Impact

Total Additional Costs: $95,000

Total Cost Savings: $15,000

Net Change to Contract Value: $80,000

6.3 Revised Contract Value

Original Contract Value: $275,000

Change Order Value: $80,000

New Total Contract Value: $355,000

6.4 Payment Terms for Change Order

Payment for this change order shall be made according to the following schedule:

Phase 2 Completion: $50,000 due upon acceptance of mobile app beta

Final Payment: $30,000 due upon completion of all change order deliverables

# 7. REVISED DELIVERABLES

7.1 Updated Deliverable Schedule

The following deliverables are affected by this change:

7.1.1 Modified Existing Deliverables

## - Technical Architecture Document:

Original Due Date: March 15, 2024

New Due Date: March 29, 2024

Specification Changes: Enhanced to include mobile backend and analytics platform architecture

7.1.2 New Deliverables

## - Real-time Analytics Dashboard:

Description: Web-based dashboard with 15 KPIs, real-time data feeds, and automated reporting

Due Date: June 15, 2024

Acceptance Criteria: Functional dashboard meeting performance requirements with user training completed

## - Mobile Application Package:

Description: Native iOS and Android applications with core functionality and app store submission

Due Date: July 30, 2024

Acceptance Criteria: Apps approved for distribution with full testing documentation

7.2 Deliverable Dependencies

The revised deliverables have the following dependencies:

Mobile applications depend on completion of enhanced backend API development

Analytics dashboard depends on successful data integration with existing systems

App store approval process may impact final delivery timeline

7.3 Quality Standards

All revised and new deliverables shall meet the same quality standards as specified in the Original SOW, with the following additions:

Mobile applications must pass security testing and performance benchmarks

Analytics dashboard must meet specified response time requirements under load

# 8. APPROVAL AND AUTHORIZATION

8.1 Change Order Authorization

This Change Order requires approval from the following authorized representatives:

8.1.1 Client Authorization

Primary Approver: Michael Chen, Chief Technology Officer

Secondary Approver: Sarah Johnson, Project Manager

Budget Authority: Michael Chen, Chief Technology Officer

8.1.2 Vendor Authorization

Project Manager: David Rodriguez, Project Manager

Account Manager: Jennifer Kim, Account Manager

Executive Sponsor: Robert Thompson, Vice President

8.2 Approval Process

This Change Order follows the approval process outlined in Section 9.2 of the Original SOW:

1. Change request submitted by Michael Chen

2. Impact analysis completed by David Rodriguez

3. Review and approval by authorized representatives

4. Implementation upon full execution

8.3 Implementation Timeline

## Upon full execution of this Change Order:

Implementation Start Date: February 5, 2024

First Modified Deliverable Due: March 29, 2024

Change Order Completion: August 15, 2024

8.4 Communication Plan

All stakeholders will be notified of this change according to the project communication plan, including:

Project team notification: February 2, 2024

Stakeholder briefing: February 5, 2024

Updated project documentation: February 8, 2024

# SIGNATURE BLOCK

CLIENT: Acme Corp

By: _________________________    Date: ___________

Name: Michael Chen

Title: Chief Technology Officer

Budget Authority: _________________________    Date: ___________

Name: Michael Chen

Title: Chief Technology Officer

VENDOR: TechSolutions Inc.

By: _________________________    Date: ___________

Name: David Rodriguez

Title: Project Manager

Project Manager: _________________________    Date: ___________

Name: David Rodriguez

Title: Project Manager

## Document Control:

Template ID: TYPE_CHANGEORDER_Standard_v1

Version: 1.0

Original SOW Reference: SOW-AC-DT-2024-001

Change Order Number: CO-001

Created: January 30, 2024

Last Modified: January 30, 2024

Next Review: August 15, 2024